## Sheet1
Internship Work Report by Jyotsna Shenoy
Dec'17 - Jan'18
| # | Task Description | Date of Assignment | Deadline | Date of Submission
| Task 1 | 50 MCQs in a single record file (entry task) | 2017-12-07 | 2017-12-14 | 2017-12-09
| Task 2 | 5 Op-amps based projects with simulation and explanation | 2017-12-16 | 2017-12-26 | 2017-12-22
| Task 3 | 4 Microcontroller projects with simulation and explanation | 2017-12-27 | 2018-01-04 | 2018-01-03
Day | Date | Summary | Number of hours | Work description
Friday | 2017-12-08 | Task 1 |  | Drafted a report file of MCQs pertaining to various disciplines in Electronics/Electrical Engineering, like Integrated circuits, Microcontrollers, Digital Communication etc.
Saturday | 2017-12-09 | Documentation of Task 1
Saturday | 2017-12-16 | Task 2 - Simulation 1, 2 and 3 | 3 | Designed circuits, constructed its schematics and performed debugging using Spice coding for different types of analysis and simulation of the same on a simulator and observed the output results. Software simulator used here is LTSpice.
Tuesday | 2017-12-19 | Task 2 - Simulation 4, 5 | 3
Thursday | 2017-12-21 | Documentation of work done till date for Task 2 | 3 | Drafted report files of written explanation with content subdivided and illustrated with images and screenshots of the output obtained by performing the successive simulations.
Wednesday | 2017-12-27 | Task 3 - Simulation 1, 2 | 3 | Designed circuits, constructed its schematics on circuit simulator Proteus 8 Professional. Microcontrollers being the centre of every project in this task, a code was prepared in Kiel MU Vision, a code simulator which has Microcontroller and C programming compatibility. After simulating, successfully debugging and building a code target, the code was converted into hex file with the code simulator. The hex file link was then burnt into the microcontroller of the circuit after which the circuit project was simulated and the output was observed with the code characteristics and the circuit design, and the same was recorded.
Saturday | 2017-12-30 | Task 3 - Simulation 3, 4 | 3
Tuesday | 2018-01-02 | Documentation of work done till date for Task 3 | 3 | Drafted report files of written explanation with content subdivided and illustrated with images, screenshots and GIFs (using LICEcap software) of the output obtained by performing the successive simulations.
Wednesday | 2018-01-03 | Documentation of work done till date for Task 4 | 3
|  | Total number of hours | 21